## Working route
Blackboard Group No 04 Class ZII | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2023-11-23 | Thursday Nov.23 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | -343 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-12-15
Each Team member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files |  | Saturday Nov.25 | TO DO | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details
Team Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Sunday Nov.26 | TO DO | review progress, refine Plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Thursday Nov.30 | TO DO | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Dec.14 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Tuesday Dec.13 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.12 | TO DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Nov.27 |  | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Thursday Nov.30 |  | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Tuesday Dec.5 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Tuesday Dec.13 | TO DO
Bahareh Baghizadeh Fundamental | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | I will deliver fundamental subprocess, and it will be measured by the documentation and step by step working on it , and after completing the individual testing , it is considered done | 3 hours | Sunday Nov.26 | done | create two different arrays . one of them can store a string that user inputs , and another array can store a number (user also input), this number will be the position of a character . then print the character in its position in that string . | I commented the program so it is understanding for all users to input their data properly , so the program is going to be compiled and tested before releasing , so it is expected that the program works properly and can manage the user input and result an rxpected output. | 5 hours | Friday Dec.1 | done | Measuring the length of two strings were created at version 1 , so in order to measure them , using the strlen( ) for measuring the length and then using strcmp() to compare the length of two strings | using git version control system , with installing , configurating and initializing git , then running git and adding "fundamentals.c" and Fundamentals.h to the repository | 3 hours | Wednesday Dec.6 | doing | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Wednesday Dec.14 |  |  |  |  | Tuesday Dec.13
[Jonathan B. Ladera] Manipulations | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | I volunteered to do the string manipulations part to implement and develop the code and coordinated with the group member thru MS Teams and planned to disseminate our task. | 3 hrs | Sunday Nov.26 | TO DO | Create an character array that can store strings, concatenates them, and prints the result until the user enters 'q' to quit | The manipulating program must correctly concatenate as intended and can handle user input appropriately including the termination condition until the user choose to quit. | 3 hrs | Friday Dec.1 | DONE | Design the string concatenation algorithm |  |  | Wednesday Dec.6 |  | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Wednesday Dec.14 |  |  |  |  | Tuesday Dec.13
[Elaine Camille Javier] Tokenizing | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | Decided on the team members and each delegation. I was assigned Tokenizing. We decided to meet at least 2x a week in person to reiterate which tasks and responsibilities we would have. | 3.5 | Sunday Nov.26 | DONE | Checked my assigned task and read the code to be transferred to a compiler. Retype the given code and use Visual Studio to compile. | Copied the code from the Week 11 file. I then used VS to write the code there and made a comment. After which, I compiled and debugged before I submitted to the Tester. | 3.5 | Friday Dec.1 | DONE | Check V2 of the project, retype and compile. Run the program and manipulate and do test phrases based on the required paramaters, isolate results and tally each based on the outcome | Used tools and software planning aids such as Git, Gitbash and even Teams/Excel, etc. Ran the Version2 of tokenizing. Checked each element and strings if different data input would generate different results | 5 hours | Wednesday Dec.6 | DONE | Furnish Version 3, |  | 6 hours | Wednesday Dec.14 | TO DO |  |  |  | Tuesday Dec.13
[Loc Dang] Conversions Team Leader | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | I understand what to be done in the Conversion module Everyone understands the project Everyone agrees on their responsility A team lead is selected | 2 hours | Monday Nov.27 | DONE | wrote a code that takes a numeric string input and convert it to an interger Comment properly on the code Compile the code | The source code will have comments to explain the algorithm. The souce code compiled successfully into an executable file that anyone can run The module converts any numeric string to the equivalent interger The module should pass the positive tests by the tester | 2 hours | Saturday Dec.2 | DONE | write and compile the code for the converting module run nominal tests produce the git-log file for converting module | The code is well-commented and compile sucessfully The code passes the nominal test The git-log file shows the changes relating to the converting module | 2 hours | Thursday Dec.7 | DONE | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Thursday Dec.15 |  |  |  |  | Wednesday Dec.14
[Dong Ngo] Testing | use PuTTy(Linux) for the compiler, I will use the main file that the team leader has done and test it. Then I create a board that includes positive cases and negative cases. | beware of confirmation bias. Each test case step results in PASS or FAIL.In the latter case, unexpected output, the lack thereof, or system error messages must be capturedand recorded. Test cases must be specific enough to be repeatable by the programmer who receivesthe testing results. | 3 hours | Sunday Nov.26 | DONE | receive my teammate c code file and start to compiler each cases | I will put my record into a board that already seperate the cases with description | 5 hours | Thursday Dec.7 | DONE | Add the capture of this version's testing to the previous "module"-testing.txt file.It is not necessary to repeat the previous version's tests in addition to the new version'stests because our project does not modify any code in the previous version.Normally, assuming new code will not affect existing code is a bad assumption in professionalpractice. Unanticipated side-effects do sometimes occur and are a frequent cause of bugs inindustry. Automated comprehensive testing is run in industry to ensure the previousapplication version has not been adversely affected by the new version. | finding a lot of fails phases cover norminal cases, edge cases and negative cases. | 5 hours | milestone upload to Blackboard | DONE |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[6 empty] | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.